## TX Example
New Disorder LIMS Implementation: [Disorder]
State NBS Program: [Program]
Project Manager: [Name]
Item | Description | Status | Estimated Duration | Start Date | Target Date of Completion | Actual Completed Date | Comments
1 | Pre-Work
1.1 | Finalize Scope of Work
1.2 | Amend LIMS Contract (if necessary)
1.3 | Develop Project Timeline
1.4 | Refresh Test Environment(s)
1.5 | Configure Test System for Assay/Instrument Evaluation and Validation
2 | Requirements Gathering
2.1 | Data Entry
2.1.1 | Web
2.1.2 | HL7
2.1.3 | LIMS Data Entry Module
2.2 | Laboratory
2.2.1 | Plate Maps
2.2.2 | Assay Definitions / QC Rules
2.2.3 | Result Calculation Algorithms
2.2.4.1 | Instrument Interfaces
2.2.4.2 | Instrument Worklist
2.2.4.2 | Result Import
2.2.5.1 | Result Reporting
2.2.5.2 | Result Report (Mailer)
2.2.5.3 | Result Codes - Determinations
2.2.5.4 | Result Notes / Comments
2.2.5.5 | HL7 ETOR
2.2.5.6 | Determine LOINC Codes
2.2.5.7 | Communicate HL7 Changes to Partners
2.3 | Follow-up
2.3.1 | Determinations
2.3.2 | Workflows / Action Mapping
2.3.3 | Letters
2.3.4 | Define Tests, Diagnoses, Dispositions, Confirmatory Tests, and Treatments
2.3.5 | Specialist diagnostic forms
2.4 | DNA Testing
2.4.1 | Result Reporting
2.5 | Stored Queries
2.6 | Other Interfaces (Billing, Vital Stats, LTFU)
3 | Test Environment Configuration (LIMS Admin and/or Vendor)
3.1 | Configuration
3.2 | Validation
4 | Development Testing
4.1 | Preparation of Test Scripts
4.2 | NBS Program Testing and Issue Reporting
4.2.1 | Internal
4.2.2 | HL7 ETOR (each partner)
4.2.3 | Data Interfaces (Billing, Vital Stats)
4.3 | Issue Remediation and Confirmation Testing
5 | User Acceptance Testing
5.1 | Change Promotion to Staging Environment
5.2 | Full End User Testing
6 | Training
6.1 | Update of Internal and Inter-Area Workflow Maps
6.2 | Staff Training on LIMS changes
7 | Go Live Preparation
7.1 | Develop Go Live Deployment plan
7.2 | End User Completion of Test Script Documentation
7.3 | Documentation of Laboratory Management and Director Approval
7.4 | Compilation of Deployment and Rollback Scripts
7.5 | Documentation of IT Change for Advisory Board Approval of Deployment
8 | Go Live
9 | Monitor Post Go Live
9.1 | Prod Deployment Review / Confirmation
9.2 | Issue Tracking
9.3 | Issue Remediation and Confirmation Testing

## MN Example
New Disorder LIMS Implementation: [Disorder]
State NBS Program: [Program]
Project Manager: [Name]
Status | Description | Target Date of Completion | Start Date | Actual Completed Date | Comments
Pre-Work
Determine Scope of Work
Requirements Gathering
Amend LIMS Contract (if necessary)
Create General Timeline with LIMS Vendor
Copy Production LIMS to Test Environment(s)
Risk Assessment
Laboratory
Determine Plate Maps
Develop QC Rules and Documentation
Computer Updates and Configuration
Instrument Installation / Interface
Instrument Work List
LIMS Test Environment Configuration
Program Cutoffs and Logic (i.e., determine demographic influences)
Create Test Structure and Algorithm (i.e., analytes, rept code, test code, primary analyte, reflux testing, disorder name, groupID)
Setup Higher-Tier Testing (or send out)
Develop Result definitions (i.e., set up expected ranges, merge exceptions, reporting range (ADL/BDL))
Determine Testing Scenarios - Coordinate with Follow-up and Interop
Create Merge File from Instrument to LIMS - Program Data Upload in LIMS
Follow-Up
Determine Workflows
Action Mapping
Create Diagnosis Codes (using SNOMED)
Create New Disposition Codes (if necessary)
Diagnostic Forms for Specialists
Distribution Group / Referrals Needed for Specialists
Letters
Confirmation Testing
Reporting
Result Report Updates (result grid, footer notes, etc)
Interpretation Language
DNA Reporting
Interoperability ¦ HIT
Determine Disorder LOINC Code(s) and Disorder Result LOINC Answer Codes
Program/Update LOINC Codes within LIMS
Contact HL7 Submitters to Determine Testing Timeline
Test Result Messages with HL7 Submitters (i.e., test scenarios coordinated w/ Lab & FU)
Test Confirmed Case HL7 Messaging with Long-Term FollowUp (if necessary)
Query Updates / Data Dictionary
Final Materials Submitted to LIMS Vendor (e.g., mailer template, dx form, result file, instrument merge file)
Data Interfaces (billing, vital stats) (if necessary)
Connect with Internal IT (if necessary)
Data Entry ¦ Operations
Data entry Updates (if any)
Training
Update of Internal and Inter-Area Workflows and Controlled Documents (e.g., SOPs, job aids, etc.)
LIMS Changes for Staff
Before Go-Live
End to End Testing
LIMS Validation Report Complete (i.e., testing plan, scenarios and outcomes)
Approval from Laboratory Management and Director
Copy Test to Production
Compilation of Deployment and Rollback Scripts
Post Go-Live
Check LIMS to Ensure Copy Over was Accurate
Issue Tracking
Issue Remediation and Confirmation Testing

## KS Example
Main NBS Manager Contact: [Name]
Main LIMS Administrator Contact: [Name]
Main Supervisor Contact: [Name'
New Disorder: [Disorder]
Action Plan | Assigned To | Date Received | Start Date | Target Completion Date | Completion Date | General Notes | Lab Comments
Preliminary Assessment
Establish Main Points of Contacts
Cement Final Deadline
Provide Background Information on New Disorder
Comments Needing CLIA Approval (if necessary)
Involved Instruments or Middle-Ware (e.g.,Specimen Gate)
Gather Example of Data File for Instrument Parser
New Disorder's Numeric and Text Requirements for Reporting
Note All Information Mediums like Final Reporting or HL7
Coding Requirements Based on Results or Auxilirary Information (if necessary)
Decide if Project Warrants Allocating Vendor (e.g., Clinisys) Resources
Testing phase
Prepare Test Environment
Create New Disorder Test and Parser from Given Information
LIMS Administrator Testing
Manager Testing and Feedback
Analyst Testing and Feedback
Revise New Disorder based on Peer Reviews
Repeat until Staff Approval
LIMS Administrator Confirms Correct Result Report Settings
Add Pre-defined Comments
Review Final Report by Manager and Analyst
Receive Approval from NBS Staff
Install New Disorder Test in Production (but with reporting set to off)
Confirm with NBS Staff about any Workflow Issues
Go-Live
Notify Customer Service of Changes to Final Report Day Before Go-Live
Turn on Reporting for New Disorder in Production the Evening before Go-Live
LIMS Team is On-site on Go-Live Day
LIMS and NBS Staff Routinely Check Final Reports and HL7 Messages for Anomalies
LIMS Contacts NBS Staff about any Workflow Issues by EOD
Modify New Disorder in Test Environment and Receive NBS approval
Upload Re-Examined Test Code to Production
Follow-up
LIMS Contacts NBS Staff One to Two Weeks after Go-Live Date (or last test revision)
Re-Examine any Workflow Disruptions
Amend Test Code Accordingly in Test Environment and Receive Approval from NBS
Load Test to Production
LIMS Retains Periodic Contact with NBS staff